## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98
Recruiting member | 4 | 1 | 4 | 1 | 100%
Project Planning | 5 | 7 | 5 | 2 | 100%
Researching | 8 | 4 | 10 | 2 | 100%
Requirements Gathering | 17 | 2 | 17 | 2 | 100%
Interview | 19 | 1 | 19 | 1 | 100%
UML and ER Diagram | 23 | 3 | 0 | 0 | 0%
Requirements Modelling | 14 | 14 | 0 | 0 | 0%
Data Modelling | 28 | 7 | 0 | 0 | 0%
Interface Design | 28 | 7 | 0 | 0 | 0%
Development | 35 | 40 | 0 | 0 | 0%
Testing | 35 | 7 | 0 | 0 | 0%
Component-level Design | 42 | 7 | 0 | 0 | 0%
Revise | 49 | 7 | 0 | 0 | 0%
Debugging | 56 | 7 | 0 | 0 | 0%
Testing | 63 | 7 | 0 | 0 | 0%
Metric Measurement | 70 | 7 | 0 | 0 | 0%
Presentation | 77 | 7 | 0 | 0 | 0%
Repolishing Project | 84 | 7 | 0 | 0 | 0%
Database Design | 42 | 7 | 0 | 0 | 0%
Profile Management Modules | 38 | 4 | 0 | 0 | 0%
Item Management Modules | 40 | 4 | 0 | 0 | 0%
Process Management Modules | 42 | 4 | 0 | 0 | 0%
Data Dictionary | 75 | 2 | 0 | 0 | 0%
Final Testing | 74 | 4 | 0 | 0 | 0%
Final Report | 77 | 4 | 0 | 0 | 0%